## Project_Workflow
Project Workflow
Milestone | Task | Stage | Status | Deliverables | Stakeholder | Timeframe/Duration | Comments
1 | Project Workflow | Plan | Completed | PACE Workflow Document - Project Scope and objectives outline, Initial project Timeline and milestone chart | HR, Leadership, Data Team | 1 Day Completed 3/2/25
2 | PACE Strategy | Plan | Completed | PACE Strategy Document - Internal planning document providing a structured approach to planning, analyzing, constructing, and executing a data-driven strategy to predict employee turnover at Salifort Motors. | Data Team | 1 Day Completed 3/2/25 | Produce in MS Word and Include a summary version in the following worksheet tab
3 | Project Proposal | Plan | Completed | Project Proposal - Formal document outlining the project's objectives, methodology, expected outcomes, and key deliverables. | HR, Leadership | 1 Day Completed 3/2/25 | Produce in MS Word
4 | Data Exploration and Cleaning | Analyse | Completed | Data Dictionary - a structured reference document that defines and describes the variables, data types, meanings, and relationships within a dataset. Cleaned Dataset - preprocess and export cleaned dataset (handle missing values, duplicates, and outliers). Python Assest - jupyter notebook detailing full process | Data Team | 1 Day | For Milestone 4 and 5, consolidate tasks into a single Jupyter Notebook and utilize the action items worksheet for structured task planning.
5 | Visualization and EDA | Analyse | Completed | Python Asset - Visualize relationships between variables of interest within the data. Tableau Asset - Create an interactive Tableau Dashboard summarizing key trends, visualizations, and correlations related to employee turnover. | Data Team, HR | 3 Days | Use action items worksheet to plan Tableau specific tasks. Tableau asset is not specifically requested. Complete this when time allows.
6 | Logistic Regression | Construct | Completed | Python Asset - Jupyter notebook detailing training and evaluation of model (Encode categorical variables, and perform feature engineering if required). | Data Team | 1 Day | For Milestone 6, create a separate Jupyter Notebook to keep the workflow concise and reduce the complexity of a fully combined notebook.
7 | Decision Tree | Construct | Completed | Python Asset - Jupyter notebook detailing training and evaluation of model (Encode categorical variables, and perform feature engineering if required). Feature Importance Analysis | Data Team | 1 Day
8 | Random Forest/XGBoost | Construct | Completed | Python Asset - Jupyter notebook detailing training and evaluation of models (Encode categorical variables, and perform feature engineering if required). Feature Importance Analysis Final Comparison of Models - Determine champion model | Data Team | 2 Days
9 | Executive Summary | Execute | Completed | Executive Report - Develop the Final Report and Recommendations for HR and leadership. | HR, Leadership, Data Team | 1 Day | Create final presentation in Canva

## P.A.C.E
P.A.C.E Strategy Summary
[Link to full PACE Document Here]
[Link to Project Proposal Here]
Employee Turnover Prediction at Salifort Motors
Overview
Salifort Motors is experiencing a high employee turnover rate, which is costly and impacts workplace morale. To address this, predictive modeling will be used to analyze survey data and determine key factors influencing attrition. This will help HR and leadership implement targeted retention strategies.
Stakeholders
HR: Interested in actionable insights for retention strategies.
Senior Leadership: Concerned with strategic decisions and high-level findings.
Data Team (Myself): Responsible for execution, model development, and reporting.
Plan Stage: Understand your data in the problem context
HR and senior leadership at Salifort Motors are the primary audience for this project. The goal is to identify key drivers of employee attrition and develop predictive models to forecast turnover risk. This involves understanding what factors contribute most to employee turnover, how accurately the risk of departure can be predicted, and what strategies HR can implement to improve retention. To complete this project, various resources are required, including Python, Jupyter Notebook, Tableau, a survey dataset, and machine learning libraries such as Scikit-Learn and XGBoost. The final deliverables will include a cleaned dataset, a Tableau EDA Dashboard, predictive models, a feature importance analysis, and a final report with recommendations.
Analysis Stage: EDA, check model assumptions & select model
The EDA process will begin with summarizing key statistics of each variable, identifying missing values, and handling inconsistencies. Correlations between employee attributes and turnover will be visualized to extract meaningful insights. Assumptions include the possibility that high workloads and long hours contribute to higher turnover, that some departments may have higher attrition rates, and that certain job roles might be more prone to leaving due to career growth limitations.
Construct Stage: Construct & evaluate models
The predictive modeling phase will involve Logistic Regression, Decision Tree, Random Forest, and XGBoost. Models will be evaluated based on accuracy, precision, recall, F1-score, and AUC-ROC. The process will include splitting the data into training and test sets, applying feature scaling and encoding where necessary, training and comparing multiple models, tuning hyperparameters for optimal performance, and interpreting feature importance to understand key drivers of attrition.
Execute Stage: Interpret models & share story
Key insights from the models will highlight which job roles, project loads, and working hours significantly impact turnover. Specific departments with higher attrition rates will be identified, and it will be observed that employees working excessive hours are more likely to leave. Based on these findings, business recommendations will focus on implementing workload balancing strategies, strengthening professional development programs, and improving employee engagement and support initiatives. Insights will be shared through a Tableau Dashboard for EDA, a final report summarizing key findings and recommendations, and a presentation to HR and leadership outlining actionable strategies.

## EDA_Cleaning
EDA & Cleaning
| Assignment Goal: | Ensure data integrity and analysis readiness by documenting dataset attributes, preprocessing data for accuracy, and maintaining a structured record of the data processing workflow.
| Action Items: |  |  | Comments:
| Dataset Dictionary |  | Completed | Gather information about the dataset including - number of columns, rows, link to dataset source, and a table of column names, data type, column description
| Create 3 Jupyter Notebooks |  | Completed | EDA/Cleaning, Logistic Regression, Tree based models. NOTE: I might keep all models together in one Notebook.
| Preliminary Data Exploration |  | Completed | Gather basic information, descriptive statistics, and general relationships
| Data Cleaning |  | Completed | Standardize columns, entries, data types, and check for missing values, duplicates, outliers
| Export Cleaned Dataset |  | Completed | Export cleaned dataset for use in model building stages
| Feature Engineering |  | Completed | Conduct comprehensive feature engineering by exploring potential combination of variables to create new insights.
| Data Visualizations and in-depth EDA |  | Completed | Continue EDA by examining variables of interest creating plots that visualize relationships between variables in the data.
| Create Tableau Dashboard (optional) |  | Not Started | Unrequested task to be completed as time allows. The goal of this task is simply aimed at practicing and refining dashboard creation skills.
| Enter Action Item Here |  | Not Started | Enter Comments Here
Additional Info/Tasks
FALSE

## Dataset_Dictionary
Dataset Dictionary
This Dataset Contains:
14,999 rows — each row is a different employee's self-reported information
10 columns
Link to Kaggle Dataset here: | [Hr Analytics Job Prediction]
Column name | Type | Description
satisfaction_level | int64 | The employee’s self-reported satisfaction level [0-1]
last_evaluation | int64 | Score of employee's last performance review [0–1]
number_project | int64 | Number of projects employee contributes to
average_monthly_hours | int64 | Average number of hours employee worked per month
company_tenure | int64 | How long the employee has been with the company (years). Changed from 'time_spend_company'
work_accident | int64 | Whether or not the employee experienced an accident while at work
left | int64 | Whether or not the employee left the company
promotion_last_5years | int64 | Whether or not the employee was promoted in the last 5 years
department | str | The employee's department
salary | str | The employee's salary (low, medium, or high)

## Tableau_Dashboard
Tableau Dashboard
Assignment Goal:
| Action Items: |  | Comments:
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
Additional Info/Tasks
FALSE

## Model_Development
Model Development
| Assignment Goal: | Develop both statistical (logistic regression) and machine learning models (decision tree, random forest, XGBoost), and evaluating their performance to identify the champion model that best balances predictive accuracy, interpretability, and business alignment for targeted HR retention strategies.
| Action Items: |  |  | Comments:
| Model Assessment and Preparation |  | Completed | Assess class balance, outliers, etc., in preparation for model development.
| Logistic Regression |  | Completed | Build and train logistic regression model
| Build and Train Tree-based Models: Round 1 |  | Completed | Build and train 3 tree based models: Decision tree, Random Forest, XGBoost
| Assess Models and Features |  | Completed | Assess model performance and if further feature engineering is required.
| Build and Train Tree-based Models: Round 2 |  | Completed | Conduct a second round of model development focused either on new hyperparameters or if there are new features created, focus on those.
| Model Evaluation |  | Completed | Perfomance metrics, confusion matrix, ROC curve analysis, and determine Champion model
| Use Champion Model on Test Data |  | Completed | Evaluate results and visualize feature importance
| Executive Report |  | Completed | Summarize key findings for HR and leadership in a concise and an easy to understand report
Additional Info/Tasks
FALSE